## Read Me
The Construction Bookkeeper — Field Kit
Editable copies of the seven tools printed in the book. Paperkeel Press.
How to use this workbook
Blue text is something you type. Black text is a formula — leave it alone.
Yellow cells are the ones to fill in first on each sheet.
Every sheet carries one example row in grey so you can see the expected format. Delete it.
Sheet | What it does
Client Setup Checklist | The seven-point configuration from Chapter 12.
Billings vs Contract | One sheet per job. Contract sum, change orders, billed to date, remaining.
Retainage Release | Both directions — held from your client, and held by your client from subs.
Overhead Recovery Rate | Last year in, this year’s rate out, with every base labelled.
Job Close-Out | Actual against estimate, line by line, feeding the next quote.
Subcontractor Register | Credentials, expiries, tax records.
Pricing and Scripts | Tier lines and client sentences on one page.
A boundary worth keeping
These are bookkeeping working papers, not accounting policy. Deposit treatment, revenue
recognition, work-in-progress and worker classification belong to the client’s CPA or tax
adviser, informed by the contract, the method and the jurisdiction. The book says where to stop.

## Client Setup Checklist
Client Setup Checklist
Chapter 12. Tick each line once it is configured and tested.
# | Configuration step | Done | Note
1 | Job tracking enabled; naming convention set (code + name, e.g. HEN-24 Henderson Kitchen); finished jobs archived. | No
2 | Chart of accounts mirrors the five cost codes — materials, labor, subcontractors, equipment, other direct — with overhead cleanly separate. | No
3 | Deposit or contract-liability workflow established under the client’s documented policy; receipt-and-release cycle tested once. | No
4 | Retainage subledger established; conditional and unconditional rights separated; subcontractor holdbacks tracked; release conditions and dates documented. | No
5 | Billings-versus-contract table built per active job (contract sum, change orders, billed to date, remaining, outstanding). | No
6 | Bill entry configured so the job field is required or unmissable. | No
7 | Monthly report pack templated: job profitability, cost-versus-budget by code, aged billings, retainage schedule. | No
| Configured | 0 of 7

## Billings vs Contract
Billings vs Contract Tracker
Chapter 7. One sheet per job. Fill the yellow cells; the rest computes.
Job | HEN-24 Henderson Kitchen
Original contract sum | 95000
Retainage rate | 5%
Line | Amount | Date | Paid? | Days out | What stage it represented
Change order 1: second vanity connection | 400 | 2026-03-02 | Yes
Deposit (received; treatment per policy) | 9500 | 2026-01-14 | Yes
Billing 1 — framing stage | 28500 | 2026-02-18 | Yes
Billing 2 — services stage | 28500 | 2026-03-20 | No | 201
Adjusted contract sum | 95400
Billed to date (including deposit) | 66500
Remaining to bill | 28900
Retainage withheld to date | 1425
Outstanding (sent, unpaid) | 28500
Example row shading is grey — replace it with the real job and delete what you do not need.
Formulas:
Days out = IF([Paid?]="Yes","",IF([Date]="","",TODAY()-DATEVALUE([Date])))
Note on B6: Percentage the customer may hold back under the contract. Enter 0.05 for 5%.

## Retainage Release
Retainage Release Schedule
Chapter 8. Both directions. Conditional and unconditional kept apart.
Job / subcontractor | Direction | Billing amt | Rate | Retained | Release condition | Expected date | Status
HEN-24 Henderson Kitchen | Held from us | 28500 | 5% | 1425 | Final sign-off | 2026-06-30 | Conditional
HEN-24 Henderson Kitchen | Held from us | 28500 | 5% | 1425 | Final sign-off | 2026-06-30 | Conditional
Marco Tile — HEN-24 | We hold from sub | 12000 | 5% | 600 | Defects period ends | 2026-07-31 | Conditional
|  |  | Total held from us | 2850
|  |  | Total we hold from subs | 600
|  |  | Net retainage exposure | 2250
Classification between receivable and contract asset is the client’s accountant’s call. This schedule records the facts, not the policy.

## Overhead Recovery Rate
Overhead Recovery Rate
Chapter 6. Built once a year. Every percentage names its base.
Inputs — last year, from the books
Vehicle and trailer (fuel, insurance, repairs) | 19400
Storage or workshop rent | 14200
General liability and equipment insurance | 8100
Phone, software, bookkeeping, registrations, small tools | 18300
Total annual overhead | 60000
Expected direct costs this year | 250000
Target operating margin on revenue | 10%
Outputs — name the base every time
Overhead markup on direct cost | 24% | Overhead ÷ direct cost. A markup, not a margin.
Break-even revenue | 310000 | Direct cost + overhead. No profit in it.
Break-even gross margin on revenue | 19.35% | Overhead ÷ break-even revenue.
Revenue needed for the target margin | 344444.4444 | Guarded: a 100% target would divide by zero.
Operating profit at that revenue | 34444.4444 | Revenue less direct cost less overhead.
Check — operating margin on revenue | 10% | Must equal the target above.
A quoting tool built from the client’s own history. Not an allocation policy for financial statements, and not a tax position.

## Job Close-Out
Job Close-Out Report
Chapter 4. Actual against estimate, line by line. This page prices the next quote.
Job | HEN-24 Henderson Kitchen
Original contract sum (as quoted) | 95000 | The quote you priced against.
Final contract income (incl. change orders) | 95400 | What the job actually billed.
Cost code | Estimated | Actual | Variance | Variance % | What the variance taught us
Materials | 29000 | 31900 | 2900 | 10%
Labor | 22000 | 24600 | 2600 | 11.82%
Subcontractors | 17500 | 17400 | -100 | -0.5714%
Equipment and plant | 1800 | 1900 | 100 | 5.556%
Other direct costs | 1300 | 1400 | 100 | 7.692%
Total cost | 71600 | 77200 | 5600 | 7.821%
Quoted gross profit (vs original sum) | 23400
Quoted gross margin on revenue | 24.63%
Actual gross profit (vs final income) | 18200
Actual gross margin on revenue | 19.08%
Margin lost between quote and close-out | 5.554%
Carry the right-hand column into the next quote. That is the whole point of the page.

## Subcontractor Register
Subcontractor Compliance Register
Chapter 9. Credentials, expiries, tax records. Expiry flags are formulas.
Subcontractor | Trade | W-9 on file | Licence expiry | Insurance expiry | Days to expiry | Flag | Notes
Marco Tile Co. | Tile | Yes | 2027-02-28 | 2026-11-30 | 54 | Due soon
Riverbend Plumbing | Plumbing | Yes | 2027-06-30 | 2027-01-15 | 100 | OK
Oak & Iron Electrical | Electrical | No | 2026-12-31 | 2026-10-31 | 24 | Renew now
Expired or missing |  | 1
Logging a certificate is bookkeeping. Judging whether the cover is adequate is the insurer’s job, and classification is the tax adviser’s.
Formulas:
Days to expiry = IF(OR([Licence expiry]="",[Insurance expiry]=""),"",MIN(DATEVALUE([Licence expiry]),DATEVALUE([Insurance expiry]))-TODAY())

## Pricing and Scripts
Pricing and Scripts Card
Chapter 13 and 15. Tier lines and client sentences, on one page.
Tier | What it includes | Monthly fee
Tier one — Records | Transactions current, bank reconciled, monthly profit and loss. The business, not the jobs. | 420
Tier two — Job Visibility | Everything in tier one, plus job costing, the billings table, and a one-page job profitability report per active job. | 850
Tier three — Job Visibility + | Everything in tier two, plus the retainage schedule in both directions, cost-versus-completion flags, and a monthly owner conversation. | 1250
Illustrative figures from the book. Replace with your own market’s numbers.
When | What to say | Chapter
Tier difference | Tier one records your business; tier two shows you which jobs make money. | 13
Value anchor | The monthly fee is small beside one repriced quote or one recovered retainage balance. | 13
Scope, not discount | If the price needs to come down, let’s decide together what comes out of the scope. | 13
Annual review | Your file has grown by two jobs and three subcontractors this year. Here is the new tier price, effective from March, so you have it in advance. | 13
Existing-client upgrade | Your books currently tell you how the business went each month. I can make them show which jobs made money. Want me to set that up? | 15
Snapshot pitch | Give me one finished job. I’ll rebuild its costs properly and show you exactly what it really made. Thirty minutes to walk it through. | 15
Credibility answer | The specialization is recent — the systems are the industry’s standard ones. Here’s a close-out report so you can see exactly what you’d get. | 15
Deposits — escalate | Before I post this, I need your accountant’s position on deposit treatment under your method. I’ll track it per customer either way. | 7
Retainage — escalate | I’ve separated the retainage into its own subledger. Your accountant should confirm which balances are receivables and which are contract assets. | 8
Worker status — escalate | Three things about this arrangement look like the control indicators the IRS considers. I’m not able to make that call — it’s worth asking your tax adviser. | 9
Insurance — escalate | I’ve logged the certificate and its expiry date. I can’t confirm the coverage is adequate for this work — that’s a question for your insurer. | 9